Example Statement of Work (SOW)

1. Background

[Insurance Client Name] is executing a major transformation to modernise its core insurance operations through the implementation of a new technology platform. This programme is expected to improve operational efficiency, strengthen risk controls, enhance customer experience, and streamline processes across Claims, Underwriting, Policy Servicing, and Support Functions.

To ensure successful adoption across the organisation, dedicated change management and communications support is required to prepare employees, mitigate risks to transition, and maintain engagement throughout the programme lifecycle.

2. Objectives

This engagement aims to:

- Build understanding, awareness, and acceptance of upcoming changes.

- Ensure leaders, managers, and employees are prepared for new processes and technology.

- Deliver clear, timely, targeted communications aligned to programme milestones.

- Support the organisation in achieving high adoption and minimising operational disruption at go-live.

- Provide insight-driven recommendations throughout the delivery lifecycle.

3. Scope of Services

3.1 Change Management

- Change Strategy & Approach
Develop an overarching change management approach tailored to the insurance operating environment, covering people impacts, behavioural changes, and role transitions.

- Change Impact Assessment
Identify how processes, systems, and roles will change across each business area, documenting impacts and required interventions.

- Stakeholder Engagement
Map stakeholders, define engagement strategies, and prepare tailored approaches for senior leaders, managers, and frontline teams.

- Change Readiness & Tracking
Establish readiness metrics, run pulse checks, and report adoption risks and themes to programme leadership.

- Change Network Mobilisation
Recruit, onboard, and equip a network of change champions to support message reinforcement, feedback gathering, and local mobilisation.

3.2 Communications

- Communications Strategy
Create a comprehensive communications plan aligned to programme phases (design, build, test, UAT, go-live, hypercare).

- Key Messaging & Narrative Development
Build a programme narrative explaining purpose, benefits, timelines, and expectations in accessible, user-friendly language.

- Content Development
Produce communication materials such as:

  - Leadership briefings

  - Email campaigns

  - Intranet articles

  - FAQs

  - Readiness updates

  - Countdown communications

  - Visual and infographic-based content

- Channel Management
Partner with internal comms teams to utilise enterprise channels effectively, ensuring messages reach the right audience at the right time.

4. Deliverables

The following deliverables will be produced during the engagement:

- Change Strategy & Delivery Plan

- Stakeholder Map & Engagement Plan

- Change Impact Assessment

- Programme Narrative & Key Message Repository

- Comprehensive Communications Plan

- Weekly or Monthly Communications Content Packs

- Change Champion Toolkit & Session Materials

- Readiness Dashboard & Insights Reports

- Go-Live Communications & Hypercare Messaging

5. Out of Scope

The following activities are outside the scope of this SoW unless mutually agreed otherwise:

- System configuration or technical development

- Formal training design or delivery (beyond advisory input)

- HR policy updates or organisational restructuring activities

- External customer communications (unless explicitly agreed)

6. Ways of Working

- Work closely with the Technology, Transformation, HR, and Communications teams.

- Attend governance meetings and provide progress updates.

- Operate flexibly, responding to changes in project timelines or priorities.

- Use collaborative tooling for document sharing, reporting, and comms approvals.

7. Resource Model

| Role | Responsibilities | Effort (Estimated) |
| --- | --- | --- |
| Engagement Lead | Overall oversight, quality assurance, senior stakeholder engagement | X days |
| Change Manager | Impact assessments, readiness, stakeholder management | X days |
| Communications Lead | Communication strategy, content development, channel planning | X days |
| Communications Specialist | Asset creation, messaging, newsletter content | X days |

8. Timeline

The engagement is expected to run from [Start Date] to [End Date], covering programme phases including design, test, readiness, go-live preparation, and post-go-live support.

9. Commercials

Pricing will follow a time-and-materials or fixed-fee model depending on final scope, resourcing, and timelines. Any change to scope or effort will be reflected in a mutually agreed change request.

Example RFP request

Technology Transformation Partner

1. Background and Context

[Client name] is undertaking a multi-year technology transformation to modernise its technology landscape, improve operational efficiency, and enable scalable, customer-centric digital capabilities. The organisation is seeking a strategic delivery partner with deep experience in end-to-end technology transformation to support the design, implementation, and adoption of this change.

This transformation will span technology, operating model, data, and people impacts, and must be delivered in a way that minimises disruption to business-as-usual operations while accelerating value realisation.

2. Objectives of the Engagement

The objectives of this RFP are to appoint a partner who can:

- Define and deliver a clear, value-led technology transformation roadmap

- Modernise core platforms, applications, and integration architecture

- Improve speed, resilience, security, and scalability of the technology estate

- Enable new digital capabilities and improved customer and colleague experience

- Support organisational readiness, change adoption, and capability uplift

3. Scope of Services

Vendors are requested to propose an integrated approach covering, but not limited to, the following areas:

Strategy and Design

- Current-state technology assessment and maturity analysis

- Target-state architecture and technology vision

- Transformation roadmap, sequencing, and value case

Technology Delivery

- Platform and application modernisation (cloud, core systems, data platforms as relevant)

- Systems integration and decommissioning of legacy technology

- Security, risk, and compliance embedded by design

Operating Model and Governance

- Technology operating model design (roles, capabilities, governance, sourcing)

- Agile delivery and programme management approach

- Benefits tracking and value realisation

Change, Adoption, and Capability

- Change management and stakeholder engagement

- Training, knowledge transfer, and capability uplift

- Transition to business-as-usual ownership

4. Vendor Response Requirements

Vendors should structure their response to address the following:

- Understanding of Client Objectives
Demonstrate understanding of our strategic context, challenges, and desired outcomes.

- Proposed Approach and Methodology
Outline your end-to-end approach, including key phases, deliverables, and dependencies.

- Relevant Experience and Case Studies
Provide examples of comparable technology transformation programmes, including scale, outcomes, and lessons learned.

- Team and Resourcing Model
Describe the proposed team structure, roles, and use of onshore/offshore or partner resources.

- Change and Adoption Approach
Explain how you will ensure successful adoption, capability transfer, and sustainable outcomes.

- Commercial Model
Provide a clear commercial proposal, including assumptions, pricing structure, and optional components.

- Risks and Mitigations
Identify key delivery risks and your approach to managing them.

5. Evaluation Criteria

Proposals will be evaluated against the following high-level criteria:

- Alignment to our transformation objectives and outcomes

- Strength and practicality of the proposed approach

- Demonstrated experience in comparable transformations

- Quality and suitability of the proposed team

- Change and adoption capability

- Commercial value and flexibility

6. RFP Timelines and Process

- RFP issued: [date]

- Vendor clarification questions due: [date]

- Proposal submission deadline: [date]

- Shortlist presentations (if required): [date]

- Preferred partner selection: [date]

7. Confidentiality

All information provided as part of this RFP must be treated as confidential and used solely for the purposes of preparing a response.

Change Management is involved wherever there’s a significant impact on how people work.
This typically includes:

- Technology transformations – new systems, platforms, automation, AI, new ways of working

- Offshoring / outsourcing – moving work, changing locations, third-party delivery models

- Restructuring & org change – org design, role changes, spans & layers, mergers or carve-outs

- Process change – redesigned processes, new policies, new controls or governance

- Large transformation programmes – multi-year change, cost transformation, operating model shifts